SUMMARY REPORT
LEASE DESCRIPTION:  Wickstrom #6-12



Diversified Operating Company
LOCATION:  1980’ FSL & 610’ FWL, SWNW/4, Sec 6-T7N-R59W 


ELEV:  4961’ 

COUNTY: Weld    STATE: Colorado    API # 05-123-32065



FIELD:  Crow


Proposed TD:  7000’








Directions: W of New Raymer, CO on Hwy 14 to CO RD 86, W approx (3) miles to rig sign, S into loc.

09/10/10 – (EE) @ 7:00 AM @ 0’ & RU. (0’) - Previous 24 Hrs – Mud wt. ___, vis __ - Excell Services, Inc. Drilling Rig #3 – MIRU; Safety mtg; RU. 

09/11/10 – (EE) @ 7:00 AM @ Surf TD of 556’ & WOC. (0’) - Previous 24 Hrs – Mud wt. ___, vis 40 - Safety mtg; RU; Drl rodent holes; Spud surf @ 8:00 PM, 09/10/10; Drl 11” hole to surf TD of 556’ @ 1:15 AM, 09/11/10; Cond mud & circ; Dev surv 3/4° @ 556’; TOOH; RU csg crew; RIH w/(13) jts 24#, 8-5/8” surf csg meas 540.81’, set @ 552.81’, PBTD @ 512.04’; Safety mtg w/cementers; RU cementers; Cmnt w/(250) sxs of B3 Lite, 3% CaCl, .25 Flo-Cele, 1.13 yield, 15.2# density; PD @ 6:45 AM, 09/11/10; WOC.

09/12/10 – (EE) @ 7:00 AM @ 1707’ & Drl 7-7/8” hole. (1151’) - Previous 24 Hrs – Mud wt. 8.8, vis 27 - Safety mtg; WOC; Nip up BOP; LD pipe; TIH; Pick up DC; Test BOP; Drl plug; Drl 7-7/8” hole; Safety mtg; Serv rig; Drl 7-7/8” hole; Dev surv 3/4° @ 995’; Drl 7-7/8” hole; Dev surv 1° @ 1491’; Drl 7-7/8” hole.

09/13/10 – (EE) @ 7:00 AM @ 3757’ & Drl 7-7/8” hole. (2050’) - Previous 24 Hrs – Mud wt. 9.2, vis 28 – Safety mtg; Serv rig; Drl 7-7/8” hole; Dev surv 1° @ 2020’; Drl 7-7/8” hole; Repair rig; Drl 7-7/8” hole; Dev surv 1° @ 2518’; TIH to retrieve surv; Drl 7-7/8” hole; Serv rig; Safety mtg; Drl 7-7/8” hole; Dev surv 1° @ 3014’; Drl 7-7/8” hole; Dev surv 1° @ 3508’; Drl 7-7/8” hole.

09/14/10 – (EE) @ 7:00 AM @ 5060’ & Drl 7-7/8” hole. (1303’) - Previous 24 Hrs – Mud wt. 9.5, vis 21 – Serv rig; Safety mtg; Drl 7-7/8” hole; Dev surv 1° @ 4036’; Drl 7-7/8” hole; Repair rig; Drl 7-7/8” hole; Repair rig; Safety mtg; Repair rig; Drl 7-7/8” hole; Dev surv 1° @ 4502’; Drl 7-7/8” hole; Dev surv 2° @ 4998’; Drl 7-7/8” hole.

09/15/10 – (SM) @ 7:00 AM @ 6179’ & Drl 7-7/8” hole. (1119’) - Previous 24 Hrs – Mud wt. 8.7, vis 39 – Serv rig; Safety mtg; Drl 7-7/8” hole; Dev surv 1° @ 5524’; Drl 7-7/8” hole; Serv rig; Drl 7-7/8” hole; Safety mtg; Clean tanks; Displace hole for MU; Drl 7-7/8” hole; Dev surv 1° @ 5991’; Drl 7-7/8” hole.

09/16/10 – (SM) @ 7:00 AM @ TD of 7000’ & Wiper trip. (821’) - Previous 24 Hrs – Mud wt. 9.2, vis 63 – Safety mtg; Serv rig; Drl 7-7/8” hole; Dev surv 1° @ 6520’; Drl 7-7/8” hole; Serv rig; Cond mud & circ; ST; 

Drl 7-7/8” hole to TD of 7000’ @ 5:30 AM, 09/16/10; Cond mud & circ; Wiper trip.
09/17/10 – (SM) @ 7:00 AM @ TD of 7000’ & RU csg crew. (0’) - Previous 24 Hrs – Mud wt. 9.3, vis 65 – Wiper trip; Cond mud & circ; Dev surv 1/2° @ 7000’; TOOH for logs; RU loggers; Log well – loggers TD @ 6998’;  RD loggers; TIH; Cond mud & circ; Safety mtg; TOOH; LDDP; LDDC; RU csg crews.
09/18/10 – (SM) @ 7:00 AM @ TD of 7000’ & RDMO. (0’) - Previous 24 Hrs – Mud wt. ___, vis __ – RU csg crews; RIH (168) jts 15.5#, 5-1/2” csg meas 6968’; set @ 6980’, PBTD @ 6966.53’; RD csg crew; Cond mud & circ; Safety mtg w/cementers; Cmnt w/(180) sxs B-3 Lite, yield 1.22, 14.2# density; PD @ 4:30 PM, 09/17/10; Nip down BOP; Rig release @ 6:30 PM, 09/17/10; RDMO.

DISTRIBUTION LIST:

Diversified Operating Company
Wray (ARW, MDC, BRM)

