## 067-09845
Operator | Energen Res
Well Name: | Navajo Lake 32-5 #16-1
Legal Location: | swse 17 32n5w
API # | 05-007-06312
Comments: | This summary confirms Mark Weems' (COGCC Regional Engineer) verbal approval to proceed with operator's plan shown below. Please coordinate submittal of the information shown on the attached guidance document with Larry Coler (COGCC Permit Tech) in Denver. Larry can be reached at (303) 894-2100 Ext. 5142 if you have any specific questions on submittal requirements. Verbal approval to proceed is contingent upon the assumption that the BHL and wellbore path remain at a legal location for completion (COGCC permitting staff will evaluate prior to formal approval of the forthcoming APD Form 2 for the sidetrack wellbore). If the BHL or the productive portion of the sidetrack wellbore extend into locations that are not legal, then Energen may have to plug back or isolate portion(s) of the well that are not legal or obtain waivers from offset mineral interests. The operator is required to notify Mark Weems at the time drilling is suspended and while the rig is moving off location.
Enter Document Numbers after Passing/Approving
Coal Seam | Planned Pilot/Lateral | API EXT | Comments | Verbal Approval Date | Form 2 | Form 4 | Form 5 | Form 5A
| Planned Pilot & Lateral | 00 |  |  | 2286404 | 1598953 2532992 2532991 | 2237321 | 0000000
| Sidetrack | 01 | Due to hole and drilling issues in the pilot/mother bore a sidetrack was requested; planned window 4545-4553; because a portion of the well bore in the payzone will be outside the drilling window, an external packer will be run on the 4 1/2" prod csg to isolate pay outside the drilling window boundaries; the target BH remains the same | 2012-06-13 | 2237290 |  | 0000000
06/26/2012 The operator notified Mark Weems that they are through with drilling and the well has been completed with only one sidetrack
Note on C8: weemsm: API #
Note on D8: David Andrews: Need to develop a template statement for "filling in the blanks" when discussing verbal approvals with the operator.
Note on G8: David Andrews: Applicable in SJB only. Otherwise, individual Form 4's required for every sidetrack.
Note on I8: David Andrews: Assumes one Form 5A per well in the Fruitland Formation (all open-hole, commingled)