## WBD
Existing |  |  |  |  | KB=11' |  | Proposed
Dolph UPRR 32-1
API: 0512316165
Cmt to surf
100'
8-5/8" 24#/ft
| 12-1/4" |  |  |  |  | 662' | TOC in pipe
Fox Hills | BHP
Surface casing | 882' |  | 165 sx
[6 empty] | 1000' | Bottom of cement
[6 empty] | 4266' | TOC
Sussex | No perfs
Top | 4466' |  |  |  | 710 SX
Shannon | No perfs
Base | 5265'
[6 empty] | 5320' | Squeeze perfs
[6 empty] | 6350' | TOC in pipe
[5 empty] | 50 sx | 6600' | TOC outside pipe
[6 empty] | 6750' | Squeeze perfs
| TOC | 6790'
2 sx
7000'
Niobrara perfs | 7173-7215'
Top | 7057'
Codell perfs | 7443-7453'
Existing cement
CICR
Exisiting CICR
CIBP
| 2-7/8" 6.5#/ft | 7621' |  |  |  |  | Existing CIBP
| 7-7/8" | 7628' |  |  |  |  | New Cement
Drilling mud

## Sheet2
1 | Call foreman or lead operator at least 24 hr prior to rig move. Request that they catch and remove the plunger, isolate production equipment and remove any automation prior to rig showing up. Install perimeter fence as needed.
2 | GYRO complete JUL12.
3 | Provide notice of MIRU to COGCC field inspector as specified in approved form 6.
4 | Notify IOC when rig mobilizes to location to generate workorder for flowline removal and one call for line locates.
5 | Prepare location for base beam equipped rig
6 | MIRU, kill as necessary using clean fresh water with biocide. ND WH. NU BOP with 1-1/4" pipe rams. Unseat tubing hanger, LD.
7 | Notify cementers to be on call. Provide volumes (50sx 50/50 Poz "G" w/ 20% silica flour, 3% gel, 0.1% sodium metasilicate and 0.4% FL-52 mixed at 13.5 ppg and 1.71 yield (10"+20%), 710 sx class G w/0.25 pps celloflake, 0.4% CD-32, 0.4% ASA-301 15.8ppg 1.15 yield (11"+20%), 165 sx Type III CaCl2 cement 1.53 yield (10"+20%)).
8 | TOOH 1-1/4” production tubing. Stand back.
9 | MIRU WL. RIH gauge ring for 2-7/8” 6.5#/ft csg to 7000'.
10 | RIH CIBP, set at 7000’. PT CIBP to 2500 psi. Dump bail 2sx cement on CIBP. RD WL.
11 | TIH to 7000' using production tubing hydrotesting tubing in. Roll hole using water containing biocide. TOOH
12 | RU WL. PU CCL and 1-2' 2" 8 spf 60* phase 18.7" penetration 0.23" EHD perforating gun. RIH to 6750', shoot squeeze holes at 6750' or closest to using CCL for correlation between collars. RD WL.
13 | Initiate circulation to determine circulation through squeeze holes. Note rate and pressure.
14 | RU cement services.
15 | Pump 10 BBL preflush using mud containing biocide, 50 sx 50/50 Poz "G" w/ 20% silica flour, 3% gel, 0.1% sodium metasilicate and 0.4% FL-52 mixed at 13.5 ppg and 1.71 yield (9"+20%) followed by wiper plug for 2-7/8" 6.5#/ft tubing. Displace plug to 6350' using water containing biocide. Apply enough pressure to hold wiper plug at 6350'. WOC overnight. RD cement services.
16 | TIH to 6350'+/-. Tag plug. If below 6350', discuss with production engineer.
17 | Spot 9.0 ppg mud containing biocide from tag to 5320'. TOOH
18 | RU WL. PU CCL and 1-2' 2" 8 spf 60* phase 18.7" penetration 0.23" EHD perforating gun. RIH to 5320', shoot squeeze holes at 5320' or closest to using CCL for correlation between collars. RD WL.
19 | RU cement services. Pump 5 BBL water, 20 BBL sodium metasilicate, 5 BBL water preflush followed by 710 sx class G w/ 0.25 pps celloflake, 0.4% CD-32, 0.4% ASA-301 15.8ppg 1.15 yield (11"+20%) followed by wiper plug for 2-7/8" 6.5#/ft tubing. Displace plug to 4266'. Apply enough pressure to hold wiper plug at 4266'. WOC overnight. RD cement services.
20 | TIH to 4266' +/-. Tag plug. If below 4266', discuss with production engineer.
21 | Spot 9.0 ppg mud containing biocide from tag to 1000'. TOOH
22 | RU WL. Crack coupling or cut casing (2-7/8" 6.5#/ft) at 1000'. RD WL.
23 | Circulate hole using water containing biocide at 1.5x hole volume to remove any gas.
24 | NDBOP, NDTH.
25 | NU BOP on casing head, install 2-7/8" pipe rams.
26 | TOOH with 2-7/8" tubing, LD. Changeover to 1-1/4" pipe rams.
27 | TIH using 1-1/4" production tubing to 1000'.
28 | RU cement services. Spot 165 sx Type III CaCl2 cement with 1.53 ft3/sk yield (9"+20%) from 1000' to 662'. RD cementers
29 | PUH to 200', circulate using water containing biocide to clear tubing 1.5x hole volume. WOC 4 hrs.
30 | TIH to 662'+/-. Tag plug, if below 662', discuss with production engineer. If above 662', RDMO cementers.
31 | Spot 9.0 ppg mud containing biocide from tag to 100'.
32 | RU WL. PU and RIH 8-5/8" CIBP to 100'. Set, PT to 1000 psi for 15 min. If tests, RDMO WL and WO rig.
33 | Supervisor submit paper copies of all invoices, logs, and reports to Frantz, Sabrina.
34 | Excavation crew to notify One Call to clear excavation area around wellhead and for flowlines.
35 | Place Redi Mix cement on will call if cement top in 8 5/8” is more than 25’ below surface.
36 | Excavate hole around surface casing enough to allow welder to cut 8 5/8” casing minimum 5’ below ground level.
37 | Welder cut 8 5/8” casing minimum 5' below ground level.
38 | MIRU redimix. Use 4500psi compressive strength cement, (NO gravel) fill stubout.
39 | Spot weld on steel marker plate. Marker should contain Well name, Well number, legal location (1/4 ¼ descriptor) and API number
40 | Properly abandon flowlines per Rule 1103.
41 | Back fill hole with fill. Clean location, level.
42 | Submit Form 6 to COGCC ensuring to provide “As performed” WBD identifying operations completed.