## Procedure
REENTRY PROCEDURE
WELL NAME: | BRADBURY #1 |  |  | DATE: | 2013-03-08
LOCATION:
Qtr/Qtr: | NENW | Section: | 15 | Township: | 9N | Range: | 58W
COUNTY: | WELD |  | STATE: | CO |  | API #: | 05-123-05679
ENGINEER: | Benjamin Zapp |  |  | 7 Day Notice Sent:
| (Please notify Engineer of any major |  |  | Do not start operations until:
| changes prior to work) |  |  | Notice Expires:
OBJECTIVE: | Reenter and re-plug
WELL DATA: | Surface Csg: | 10 3/4" 32.75# H40 300' |  |  |  | KB Elevation:
| Surface Cmt: | 300xs |  |  |  | GL Elevation: | 4707
| Long St Csg: | 7 7/8" open hole |  |  |  | TD: | 7813
| Long St Cmt: | none |  |  |  | PBTD:
| Long St Date: | 1953-06-02
| Plug Info (1) |  | NO INFO ON RECORD
Plug Info (2)
Plug Info (3)
Plug Info (4)
| Tubing: |  |  |  | Rods:
Pump:
| Misc.: | Base Fox Hills 477', Deepest water well 1000'
WELL STATUS: |  | Well Abandoned 6/2/53
COMMENTS: |  | NO PLUGGING REPORT ON RECORD, PROCEEDE WITH CAUTION
PROCEDURE:
1) | Survey and locate abandoned well, mark with stake
2) | Excavate to expose top of surface casing
3) | Weld 2" collar to top of 10 3/4" surface casing cap. Make up to collar, pneumatic drill with non-sparking bit. Drill out cap venting possible trapped gas.
4) | Once verified that no gas exists beneath top of surface casing plate, cut off surface casing below plate with torch, dress up smooth.
5) | Butt weld 10 3/4" casing to dressed cut, bringing threaded end of casing to ground level.
6) | Make up to 10 3/4" casing, one 10 3/4" collar and 10 3/4" starter well head
7) | NU flange adaptor and 5k BOP, test BOP.
8) | NU and RIH with 6 7/8" cone bit, PU 2 7/8" drill collar, 2 7/8" 8.7# tubing, and TIW valve
9) | Drill out first cement plug inside surface casing, roll hole clean. Verify top of next cement plug inside of surface casing by tagging.
10) | If unable to verify isolation of surface casing with tag of cement plug, set RBP inside surface casing
11) | Once isolation of surface casing is established, either with tagging of cement plug or setting of RBP, pressure test surface casing to 200psi
12) | After pressure test of surface casing, retrieve RBP or continue drill out of cement plug under surface casing shoe.
13) | Assume pressure under surface casing shoe, roll hole with kill fluid until well dead, or blow down.
14) | Continue RIH, cleaning out with drilling mud or water to 3000'
15) | TOOH with cone bit, drill collars, and 2 7/8" tubing.
16) | PU and RIH with mule shoe and 2 7/8" tubing to 3000'.
17) | RU cement crew and pump a balanced plug of 100sk 15.8 ppg Class G "neat" cement
18) | POOH to 1150' (150' below deepest water well @ 1000')
19) | RU cement crew and pump 498 sxs of 15.8ppg Class G "neat" cement bring cement to surface
20) | POOH with 2 7/8" tubing. Wait 4 hrs, and tag TOC. If cement has fallen, top off back to surface
21) | Let cement set over night, verify cement has not settled and is still at surface. RDMO
22) | Excavate around wellhead to 8' below grade, cut off 10 3/4" casing, weld on cap
23) | Backfill hole and reclaim surface to original conditions