- NOTE: Gyro obtained 5/30/13.

- Level location for base beam rig.

- Call Foreman or Field Coordinator before rig up to catch plunger, isolate production equipment, and ask if replacement parts/equipment are requested.  Operations need to hook up the Bradenhead pressure and bleed off the pressure before the rig gets on location.

- Check and report surface casing pressure.  If surface casing is not accessible at ground level, re-plumb so valve is at ground level.

- Spot a minimum of 20 jts 2-1/16”, 3.25#, J-55 EUE TBG for replacement.

- MIRU WO rig, flat tanks and rig pumps.

- ND WH. NU BOP.

- Pressure test wellbore to 2500 psi. If pressure test holds, proceed.

- MIRU WL. Correlate depth to OWP CBL/GR dated 1/12/95. Shoot squeeze holes at 5150’. RDMO WL.

- Attempt to establish circulation down casing/up casing-open hole annulus before setting CICR. Note circulation rate, pressure, and returns without exceeding 2500 psi.

- Set CICR at 5000’. PU stinger and RIH on 2-1/16” tbg. Sting into retainer at 5000’.

- RU cementer. Prepare & pump 410 sks “G” w/0.25 pps cello flake, 0.4% CD-32, 0.4% ASA-301 mixed at 15.8 ppg and 1.15 cu ft/sk, into squeeze holes at 5000’. Displace cement to CICR. Sting out of CICR and reverse out. Design is for coverage from 5150 to 4200 in 9.3” hole, including 20% excess.

- TOOH and stand back tbg. LD stinger. WOC overnight at minimum.

- MIRU WL. PU and RIH with CCL/CBL/GR. Correlate to depth to CBL/GR. Run CBL from 5000’ to SURFACE. Deliver logs to Evans for review. Once cleared by Engineering, proceed with next step.

- TIH with 2-1/16” TBG to just above CICR/tagged depth.

- Circulate gas out of well and pressure test CSG to 2000 psi for 15 min.

- If pressure test passes, proceed.

- P&LD entire tbg string.

- ND BOP, NU frac valve.

- RDMO WO rig. Secure wellhead. Ensure that HZ SAFETY PREP SIGN IS HUNG ON WELLHEAD.

- END OF SAFETY PREP STEPS. WELL IS TO BE LEFT WITH PLUGS AND CEMENT IN HOLE.

- Once offset fracs are completed and well is cleared to RTP, MIRU WO rig.

- ND frac valve, NU BOP. PU and TIH with 2-7/8” bit on 2-1/16” TBG.

- Drill out CICR/cement down to 5200’. Role hole clean in preparation to pull RBPs.

- Pressure test casing/squeeze holes to 1000 psi. If pressure test passes, proceed.

- TOOH while standing back tbg and LD bit.

- PU and TIH with RBP retrieving head down to sand cap at ~6800’.

- Circulate sand off RBP & any gas out of well.

- Latch onto RBP and release RBP. TOOH and stand back 2-1/16” TBG. LD RBP and retrieving head.

- TOOH while standing back tbg and LD bit.

- PU and TIH with RBP retrieving head down to sand cap at ~6885’.

- Circulate sand off RBP & any gas out of well.

- Latch onto RBP and release RBP. TOOH and stand back 2-1/16” TBG. LD RBP and retrieving head.

- PU and RIH with open ended TBG and circulate clean down to 7435’. TOOH and stand back TBG.

- PU and TIH w/ 2-1/16” NC, XN profile nipple, and 2-1/16” TBG and land TBG at +/- 7266’, which is approximately 1 joint above the CD perfs.

- RU rig lubricator. Broach TBG to XN. RD rig lubricator.

- ND BOP. NU TBG head & TBG head adapter.

- RDMO WO rig. Notify Foreman or Field Coordinator of completed workover operations. Return well to production team.