## Sors 1P
GEOLOGIC PROGNOSIS
WELL LOCATION
WELL NAME: |  | Sors 1 |  |  |  |  | DATE: | 2013-12-19
API #:
COUNTY, ST: |  | Washington, CO |  |  |  |  | FIELD: | Wildcat
LOCATION: |  |  |  | SHL |  | Formation Entry |  | BHL
| Sec | Twn (N) | Rge (W) | FSL | FWL | FNL | FWL | FSL | FWL
| 26 | 4 | 54 | 650 | 650
ELEVATION: | est. GL | 4412 | est. KB | 4437
SURF. CASING DEPTH: | 1000 |  |  |  |  | This well is a vertical stratigraphic test to assess the Virgil and Missouri section, as well as the rest of the Penn to TD in the Precambrian.
ESTIMATED TVD well: | -3795
OBJECTIVE FORMATION: | Virgil/Missouri
FORMATION AT TD: | Precambrian
| Estimated tops Poros 1H* | [6 empty] | Offset Brunkhardt D 1-33
Formation Tops at SHL | md | tvd | tvdss | REMARKS |  |  |  | md | tvdss
Niobrara |  | 4188 | 249 |  |  |  |  | 4072 | 199
Carlile |  | 4512 | -75 |  |  |  |  | 4396 | -125
Greenhorn |  | 4654 | -217 |  |  |  |  | 4538 | -267
Dakota "D" Sand |  | 4968 | -531 | Potential oil shows, disposal zone |  |  |  | 4852 | -581
Dakota "J" Sand |  | 5053 | -616 | Potential oil shows |  |  |  | 4937 | -666
Morrison |  | 5468 | -1031 |  |  |  |  | 4349 | -78
Permian Salt |  | 5804 | -1367 | Salt |  |  |  | 5688 | -1417
Lyons |  | 6200 | -1763 | Not present or very thin
Stanka Shale |  | 6387 | -1950 |  |  |  |  | 6271 | -2000
Chase |  | 6427 | -1990 | Water |  |  |  | 6311 | -2040
Amazon Dolimite |  | 6534 | -2097 | Potential oil shows |  |  |  | 6418 | -2147
Council Grove |  | 6595 | -2158 |  |  |  |  | 6479 | -2208
Admire |  | 6754 | -2317 | Secondary oil target |  |  |  | 6638 | -2367
Admire C |  | 6859 | -2422 | Secondary oil target |  |  |  | 6743 | -2472
Virgil |  | 6895 | -2458 | Main oil reservoir target |  |  |  | 6779 | -2508
Missouri |  | 7196 | -2759 | Main oil reservoir target |  |  |  | 7080 | -2809
Des Moines |  | 7366 | -2929 | Potential oil shows |  |  |  | 7250 | -2979
Cherokee |  | 7604 | -3167 |  |  |  |  | 7488 | -3217
Proposed TD |  | 8232 | -3795 |  |  |  |  | 8117 | -3846
*Dip is estimated at 0.5 degrees, or ~45'/mile. This area has very limited well control. Tops may be off!
LOGGING PROGRAM
OPEN HOLE LOGS: |  | Halliburton. Logging Job 1: Run 1: Quad combo, with laterolog, from intermediate casing point to surface casing and GR/N/Sonic to surface. Logging Job 2: Run 1: Triple combo with Spectroscopy (GEM) from TD to intermediate; Run 2: Formation Imager (XRMI) and Dipole sonic (WAVE) from TD to intermediate'.
Wellsite Geologist:
LOGGING COMPANY: |  | Halliburton
MUD LOGGING: |  | Columbine Logging, log out of surface casing to TD
SAMPLES: |  | Cuttings - 30' interval above Admire. 10' interval from Admire to TD (need 2 sets)
CORING: |  | Cut 480' of whole core starting 5' above the Admire starting at -2315 and ending at -2800'
CORE HANDLING: |  | Weatherford Laboratories in Golden, CO
OFFSET WELLS
WELL NAME: |  |  | LOCATION |  |  | COUNTY |  |  | STATE
Brunkhardt D 1-33 |  | 5N-54W sec 33 |  |  |  | Washington |  |  | CO | 5 miles NW
REMARKS:
Chama CONTACTS
OPERATIONS GEOLOGIST: | TBD
Vendor CONTACTS
Mud Logging | Columbine Logging - John Tesone |  |  | 303-289-7764 ext 3007
Weatherford Labs - Core Handling | Well site coordinator - Kyle West, 720-497-8225 or cell 970-389-6718 | [6 empty] | se
Weatherford Labs - Core Handling | Well site manager - Hans Ocken, cell 303-809-7829
PLEASE KEEP THIS PROGNOSIS AND ALL RELATED INFORMATION CONFIDENTIAL (I.E DO NOT RELEASE ANY INFORMATION)

## WBS - DVD
WELLHEAD/CSG/BITs |  | Depth | Formation Top | CHAMA OIL & MINERALS LLC
FMC - Multibowl - 5K |  |  |  | Sors 1P |  | API: | 05-121-11018-00
13 3/8 x 9 5/8 x 5 1/2" |  | --- CAPPED |  | Sec 26 | T 4N | R 54W
Cement to Surface |  |  |  | 650 FSL | 650 FWL
BIT - 17 1/2" |  |  |  | Washington County CO
13 3/8" - 61 ppf BTC @ 550'
|  |  |  | Date | Days | Estimate | Actual
CAL. Cement TOP 2800' |  |  |  | 2012-12-24 | -1 | 80 | 80
|  | OBSERVED FORMATION TOP |  | 2012-12-25 | 0 | 105 | 105
BIT - 12 1/4" |  | 4108 | NIOBRARA | 2012-12-26 | 1 | 510 | 550 | 13 3/8 shoe
|  | 4471 | CARLILE | 2012-12-27 | 2 | 510 | 550
|  | 4593 | GREENHORN | 2012-12-28 | 3 | 700 | 550
|  | 4929 | DAKOTA D SAND | 2012-12-29 | 4 | 1750 | 555
|  | 5010 | DAKOTA J SAND | 2012-12-30 | 5 | 3300 | 2750
|  |  |  | 2012-12-31 | 6 | 4500 | 4080
Plug #1 TOP - 6206' |  | 5480 | MORRISON | 2013-01-01 | 7 | 5800 | 5306
|  | 5780 | PERMIAN SALT | 2013-01-02 | 8 | 6400 | 5418
|  | NP | LYONS | 2013-01-03 | 9 | 6400 | 5755
9 5/8" - 40 ppf BTC @ 6385' |  | 6330 | STANKA SHALE | 2013-01-04 | 10 | 6400 | 5755
|  |  |  | 2013-01-05 | 11 | 6490 | 5778
|  | 6404 | CHASE | 2013-01-06 | 12 | 6749 | 5945
|  |  |  | 2013-01-07 | 13 | 6800 | 6345
|  | 6510 | AMAZON DOLIMITE | 2013-01-08 | 14 | 6860 | 6385 | 9 5/8 shoe
BITs - 8 3/4" |  |  |  | 2013-01-09 | 15 | 6920 | 6385
| MUD | 6560 | COUNCIL GROVE | 2013-01-10 | 16 | 6980 | 6385
|  |  |  | 2013-01-11 | 17 | 7040 | 6385
P/U Hallibburton Core BHA |  | 6655' |  | 2013-01-12 | 18 | 7130 | 6655 | Start core
|  | 6700 | ADMIRE | 2013-01-13 | 19 | 7250 | 6745 | TOH w/C1-91'
Plug #1 Top - 6800' |  |  |  | 2013-01-14 | 20 | 7500 | 6866 | TOH C2 - 119.7'
|  | 6800 | ADMIRE C | 2013-01-15 | 21 | 7800 | 6986 | TOH C3 - 122.35
|  |  |  | 2013-01-16 | 22 | 8100 | 6986 | Insp BHA
|  | 6840 | VIRGIL | 2013-01-17 | 23 | 8220 | 7106 | C4 - 120'
|  |  |  | 2013-01-18 | 24 | 8220 | 7375 | 0
|  |  |  | 2013-01-19 | 25 | 8220 | 7758
L/D Core BHA |  | 7106' |  | 2013-01-20 | 26 | 8220 | 8250 | Circ Samples
BIT - 8 3/4" |  | 7150 | MISSOURI | 2013-01-21 | 27 |  | 8280 | RD HES Log
|  | 7320 | DES MONES |  |  | TA'd | 6250 | Top #2 6800'
|  | 7570 | CHEROKEE |  |  |  | 6206 | TOP #1 Plug
|  |  |  | 2013-01-22 | 28 |  | 6206 | RD
|  |  |  | 2013-01-23 | 29 | Rig Rel @ 1800 hrs 1/23/13
ACTUAL 8280' TD