## P&A Daily Report
Company Name: | HRM Resources, LLC |  | Company Man: | Terry Pape |  |  |  | Today's Date: | 2016-12-21
AFE or Project #: |  |  | Company Man Cell: | 970-768-5700 |  |  | Days on Well:
API # | 05-039-06646-00
Well Name/Number: | State Alberta 36-34
Section/Township/Range | SWSE Sec 36 T8S R59W
Rig #: | 6 | Drive/Hrs | Ride/Hrs | Work/Hrs | Total/Hrs | Per Diem
Tool Pusher: | Scott Marez | 1 |  | 11 | 12 | yes
Operator: | Cody Scott | 1 |  | 11 | 12 | yes
Rig Hand: | Jesus Caudillo |  | 1 | 11 | 12 | yes
Rig Hand: | Edgar Parra |  | 1 | 11 | 12 | yes
Rig Hand:
Task Times: | Job Steps "In Scope" |  |  | Task Times: |  | Job Steps "Out of Bid Scope"
|  |  |  | 6 am | 6:30 am | Crew Travel.
|  |  |  | 6:30 am | 7:30 am | Safety meeting, start equipment.
|  |  |  | 7:30 am |  | check pressures, 0/0, LD 114 JTS of TBG and took a H2S hit, over
[5 empty] | 9:30 am | 200 ppm, call Craig Owen to report it & call Mark Dawkins for
rescue packs, run and meet TJ w/Pro Treat Tech and PU
Scavenger & Biocide, take back to location and mix w/130 BBL's
water in rig tank, circulate rig tank and mix good, SWI, PU & drain
[5 empty] | 5:30 pm | up equipment, secure location.
|  |  |  | 5:30 pm | 6 pm | Crew travel.
Comments: |  |  |  | Comments:
P&A Mangers Signature: |  |  |  | VP Operations Signture:

## Example
Company Name: | Btand X |  | Company Man: | Billy Bob |  |  |  | Today's Date: | 2015-12-03
AFE or Project #: | 000-1-0 |  | Company Man Cell: | (000) 000-0000 |  |  | Days on Well: |  | 1
Well Name/Number: | New Form #1
Section/Township/Range | 21-4S-102W
Rig #: | 521 | Drive/Hrs | Ride/Hrs | Work/Hrs | Total/Hrs | Per Diem
Tool Pusher: | Johnny Doe | 2 |  | 10 | 12 | yes
Operator: | Billy Doe | 2 |  | 10 | 12 | yes
Rig Hand: | Jimmy Doe |  | 2 | 10 | 12 | yes
Rig Hand: | Greg Doe |  | 2 | 10 | 12 | Yes
Rig Hand:
Task Times: | Job Steps "In Scope" |  |  | Task Times: |  | Job Steps "Out of Bid Scope"
12
Comments: |  |  |  | Comments:
P&A Mangers Signature: |  |  |  | VP Operations Signture: