## P&A Daily Report
Company Name: |  | HRM Resources, LLC |  | Company Man: | Terry Pape |  |  |  | Today's Date: | 2016-12-22
AFE or Project #: |  |  |  | Company Man Cell: | 970-768-5700 |  |  | Days on Well:
API # |  | 05-039-06646-00
Well Name/Number: |  | State Alberta 36-34
Section/Township/Range |  | SWSE Sec 36 T8S R59W
Rig #: |  | 6 | Drive/Hrs | Ride/Hrs | Work/Hrs | Total/Hrs | Per Diem
Tool Pusher: |  | Scott Marez | 1 |  | 11 | 12 | yes
Operator: |  | Cody Scott | 1 |  | 11 | 12 | yes
Rig Hand: |  | Jesus Caudillo |  | 1 | 11 | 12 | yes
Rig Hand: |  | Edgar Parra |  | 1 | 11 | 12 | yes
Rig Hand:
Task Times: |  | Job Steps "In Scope" |  |  | Task Times: |  | Job Steps "Out of Bid Scope"
[5 empty] | 6 am | 6:30 am | Crew Travel.
[5 empty] | 6:30 am | 7:30 am | Safety Meeting, start equipment.
[5 empty] | 7:30 am | 8 am | Circulate work tank to mix Scavenger & biocide.
[5 empty] | 8 am | 9:30 am | pump 120 BBL's, caught circulation, roll hole good.
[5 empty] | 9:30 am | 10:30 am | let well set for 1 Hr.
[5 empty] | 10:30 am |  | Check for H2S, no H2S present, LD rest of TBG, ( 188 JTS of 2 7/8" )
12:30 pm | 1 pm | LUNCH. |  |  |  | 12:30 pm | changeover to 2 3/8" handling equipment, MI 2 3/8" workstring.
1 pm |  | PU bit & scraper w/bumper sub, PU TBG @ 5900', TOOH
w/TBG, finish in morning, SWI, PU & secure location, drain up
| 5:30 pm | equipment.
5:30 pm | 6 pm | Crew travel.
Comments: |  |  |  |  | Comments:
P&A Mangers Signature: |  |  |  |  | VP Operations Signture:

## Example
Company Name: | Btand X |  | Company Man: | Billy Bob |  |  |  | Today's Date: | 2015-12-03
AFE or Project #: | 000-1-0 |  | Company Man Cell: | (000) 000-0000 |  |  | Days on Well: |  | 1
Well Name/Number: | New Form #1
Section/Township/Range | 21-4S-102W
Rig #: | 521 | Drive/Hrs | Ride/Hrs | Work/Hrs | Total/Hrs | Per Diem
Tool Pusher: | Johnny Doe | 2 |  | 10 | 12 | yes
Operator: | Billy Doe | 2 |  | 10 | 12 | yes
Rig Hand: | Jimmy Doe |  | 2 | 10 | 12 | yes
Rig Hand: | Greg Doe |  | 2 | 10 | 12 | Yes
Rig Hand:
Task Times: | Job Steps "In Scope" |  |  | Task Times: |  | Job Steps "Out of Bid Scope"
12
Comments: |  |  |  | Comments:
P&A Mangers Signature: |  |  |  | VP Operations Signture: