## Sheet1
COGCC Orphan Well Program 1120 Lincoln St. Ste. 801 (303) 894-2100 (COGCC) Ext. 5105 (PM Ofc.) (970) 302-1024 (PM Cell) |  | Location Number |  | 312201 |  | DATE | 2020-02-03
[6 empty] | WELL NO. | 075-06347
|  | Contractor |  | Excell |  | HOURS | 7:30 | TO | 15:30
|  | WEATHER |  | 18 Degrees |  | COUNTY | Logan
|  | OWP Project Mgr. |  | Cal St. John |  | CUSTOMER ORDER |  | PHAA 2020 072
|  | DIRECTIONS |  | Mount Hope Green #31
TIME | DAILY WORK RECORD
7:30 | Crew start.
8:30 | Bradenhead check. No pressure 0 psig.
9:00 | MOB complete.
9:15 | Pull polish rod. Start pulling rod string.
14:15 | Complete pulling rod string.
14:30 | Prep rig to pull tubing. Install stabbing valve. Change out nipple and broken valve. Pick up and secure location.
15:30 | Shut down and depart location for meeting at Wray office.
Notes:
| Hours | Price/Hour | Total |  | POSITION | NAME | RIG | TRAVEL | TOTAL
| 0 | 0 | 0 |  | OPERATOR | Jason |  |  | 0
|  |  | 0 |  | DERRICK |  |  |  | 0
|  |  | 0 |  | CREWMAN | Sal |  |  | 0
|  |  | 0 |  | CREWMAN | Armondo |  |  | 0
|  |  | 0 |  | CREWMAN |  |  |  | 0
0
|  | 0 | 0 |  | WELL RECORD
|  | 0 | 0 |  | Type Well Head
|  | 0 | 0 |  | Packer Settings
|  | 0 | 0 |  | Type Packer
|  | 0 | 0 |  | No. Jts. Tubing
|  | 0 | 0 |  | Pump Out
|  | 0 | 0
|  | 0 | 0 |  | Size Rods | No.Rods | Size Subs | No.Sub
|  | 0 | 0 |  | 0.875" | 100
|  | 0 | 0 |  | 0.75" | 110
| Gallons | Price per Gal |  | Total | 1" |  | 6' | 1
Fuel |  |  | 0
| # of unit | Price per Unit |  | Total
|  | 0 | 0
|  | 0 | 0
|  | 0 | 0
|  | 0 | 0
|  | 0 | 0
|  | 0 | 0
|  | 0 | 0
|  | 0 | 0
Other |  |  | 0
Total |  |  | 0
On Site Task Mgr. | Cal St. John |  | Approved By: |  |  |  |  | Date: