## Sheet1
COGCC Orphan Well Program 1120 Lincoln St. Ste. 801 (303) 894-2100 (COGCC) Ext. 5105 (PM Ofc.) (970) 302-1024 (PM Cell) |  | Location Number |  | 312201 |  | DATE | 2020-02-05
[6 empty] | WELL NO. | 075-06347
|  | Contractor |  | Excell |  | HOURS | 7:30 | TO
|  | WEATHER |  | 3 Degrees |  | COUNTY | Logan
|  | OWP Project Mgr. |  | Cal St. John |  | CUSTOMER ORDER |  | PHAA 2020 072
|  | DIRECTIONS |  | Mount Hope Green 31
TIME | DAILY WORK RECORD
7:30 | Crew start.
8:15 | Rig start up. Starting issues with cold and battery.
8:16 | Prep rig and WH to start pulling tubing.
9:30 | Latch up, unseat, and start tripping tubing.
12:00 | Lunch
12:30 | Resume tripping tubing out of well.
2:20 | Tubing out of well.
2:30 | Secure well with BOP and set up pump and tank
4:30 | Pick up and secure location. Shut down for night.
Notes: | 15 stands in the derrick (944.98') and 135 joints layed down.
End of tubing string had 6' and 8' sub above Otis Log Set Packer. Below the packer there was 4' sub with seat nipple with 4' tail joint.
| Hours | Price/Hour | Total |  | POSITION | NAME | RIG | TRAVEL | TOTAL
| 0 | 0 | 0 |  | OPERATOR | Jason |  |  | 0
|  |  | 0 |  | DERRICK |  |  |  | 0
|  |  | 0 |  | CREWMAN | Sal |  |  | 0
|  |  | 0 |  | CREWMAN | Armondo |  |  | 0
|  |  | 0 |  | CREWMAN |  |  |  | 0
0
|  | 0 | 0 |  | WELL RECORD
|  | 0 | 0 |  | Type Well Head
|  | 0 | 0 |  | Packer Settings
|  | 0 | 0 |  | Type Packer |  | Otis Log Set Packer
|  | 0 | 0 |  | No. Jts. Tubing |  | 165
|  | 0 | 0 |  | Pump Out
|  | 0 | 0
|  | 0 | 0 |  | Size Rods | No.Rods | Size Subs | No.Sub
|  | 0 | 0
|  | 0 | 0
| Gallons | Price per Gal |  | Total
Fuel |  |  | 0
| # of unit | Price per Unit |  | Total
|  | 0 | 0
|  | 0 | 0
|  | 0 | 0
|  | 0 | 0
|  | 0 | 0
|  | 0 | 0
|  | 0 | 0
|  | 0 | 0
Other |  |  | 0
Total |  |  | 0
On Site Task Mgr. |  |  | Approved By: |  |  |  |  | Date: