## Sheet1
COGCC Orphan Well Program 1120 Lincoln St. Ste. 801 (303) 894-2100 (COGCC) Ext. 5105 (PM Ofc.) (970) 302-1024 (PM Cell) |  | Location Number |  | 312201 |  | DATE | 2020-02-06
[6 empty] | WELL NO. | 075-06347
|  | Contractor |  | Excell |  | HOURS | 7:30 | TO | 3:30
|  | WEATHER |  | 3 Degrees |  | COUNTY | Logan
|  | OWP Project Mgr. |  | Mike Hickey |  | CUSTOMER ORDER |  | PHAA 2020 072
|  | DIRECTIONS |  | Mount Hope Green 31
TIME | DAILY WORK RECORD
7:30 | Crew start.
7:50 | Rig start up.
8:00 | Wireline on location. Rigging up.
10:30 | Start pumping water into well at low rate for pressure test.
11:00 | Wireline complete. Set 2 plugs and set 3 sx cement on top of each plug.
11:40 | Well loaded and pressured up for pressure test. Pressure test good.
12:30 | Change Order: Rig up wire line to run CBL.
2:30 | Change Order: CBL completed.
2:30 | Wire line tool change and into well for perforations at 1050' and 419'. Rig crew draining pump and lines.
3:00 | Wire line rig down complete.
3:30 | Well and location secured. Depart location with rod trailer. SDFN.
Notes:
| Hours | Price/Hour | Total |  | POSITION | NAME | RIG | TRAVEL | TOTAL
| 0 | 0 | 0 |  | OPERATOR | Jason |  |  | 0
|  |  | 0 |  | DERRICK | Rafo |  |  | 0
|  |  | 0 |  | CREWMAN | Sal |  |  | 0
|  |  | 0 |  | CREWMAN | Armondo |  |  | 0
|  |  | 0 |  | CREWMAN |  |  |  | 0
0
|  | 0 | 0 |  | WELL RECORD
|  | 0 | 0 |  | Type Well Head
|  | 0 | 0 |  | Packer Settings
|  | 0 | 0 |  | Type Packer
|  | 0 | 0 |  | No. Jts. Tubing
|  | 0 | 0 |  | Pump Out
|  | 0 | 0
|  | 0 | 0 |  | Size Rods | No.Rods | Size Subs | No.Sub
|  | 0 | 0
|  | 0 | 0
| Gallons | Price per Gal |  | Total
Fuel |  |  | 0
| # of unit | Price per Unit |  | Total
|  | 0 | 0
|  | 0 | 0
|  | 0 | 0
|  | 0 | 0
|  | 0 | 0
|  | 0 | 0
|  | 0 | 0
|  | 0 | 0
Other |  |  | 0
Total |  |  | 0
On Site Task Mgr. | Cal St. John |  | Approved By: |  |  |  |  | Date: