## Sheet1
COGCC Orphan Well Program 1120 Lincoln St. Ste. 801 (303) 894-2100 (COGCC) Ext. 5105 (PM Ofc.) (970) 302-1024 (PM Cell) |  | Location Number |  | 312201 |  | DATE | 2020-02-07
[6 empty] | WELL NO. | 075-06347
|  | Contractor |  | Excell |  | HOURS | 7:30 | TO | 4:00
|  | WEATHER |  | 3 Degrees |  | COUNTY | Logan
|  | OWP Project Mgr. |  | Mike Hickey |  | CUSTOMER ORDER |  | PHAA 2020 072
|  | DIRECTIONS |  | Mount Hope Green 31
TIME | DAILY WORK RECORD
7:30 | Crew start.
7:30 | Rig start up.
7:45 | Tripping tubing and cement retainer into well.
8:15 | Cement retainer set at 950'.
8:40 | Excell cement crew on location. Spot in equipment and rig up to well.
9:20 | Start cement job on plug #3.
10:40 | Cement job for plug #3 compete. Rig down and clean up cement truck and rig pump. Trip tubing out of well.
11:00 | Tubing out. Lay down 30 joints to tubing float.
11:20 | Start loading well with cement truck and continue with a 5 bbl pad prior to setting surface plug
11:25 | Shut down due to shallow surface casing leak. Rig in reverse pump to pump fluids from aroud wellhead to tank.
11:40 | Start 160 sx surface plug.
12:00 | Cement to surface. Start flush and clean up cement equipment.
12:30 | Lunch.
1:00 | Start picking up and preping rig and equipment for move.
2:30 | Rig off well. Demob complete. Start Mob to next locaton.
2:30 | Use backhoe to excavate anchors. Pick up trash and debris on location. Load scrap pipe for haul off.
4:00 | Secure location and depart.
Notes: | Cement truck pump pressure could not get well to break. Rigged in rig pump and pumped 18 bbls with no break. Changed pump plan and rigged cement truck into rig pump to pump cement job.
While loading well and planned 5 bbl pad, fluids came up around surface casing. Shut down cement pump truck and rig in reverse pump. Suck up fluids around well and pump to tank. Pumped surface plug with good returns to tank and return fluids from around surface casing. Used reverse pump to pump fluids from around surface casing to tank and complete job. Shut down with cement returns to the clean up tank.
| Hours | Price/Hour | Total |  | POSITION | NAME | RIG | TRAVEL | TOTAL
| 0 | 0 | 0 |  | OPERATOR | Jason |  |  | 0
|  |  | 0 |  | DERRICK | Rafo |  |  | 0
|  |  | 0 |  | CREWMAN | Sal |  |  | 0
|  |  | 0 |  | CREWMAN | Armondo |  |  | 0
|  |  | 0 |  | CREWMAN | Jeremy |  |  | 0
0
|  | 0 | 0 |  | WELL RECORD
|  | 0 | 0 |  | Type Well Head
|  | 0 | 0 |  | Packer Settings
|  | 0 | 0 |  | Type Packer
|  | 0 | 0 |  | No. Jts. Tubing |  | 165 2 7/8" joints on trailer.
|  | 0 | 0 |  | Pump Out
|  | 0 | 0
|  | 0 | 0 |  | Size Rods | No.Rods | Size Subs | No.Sub
|  | 0 | 0
|  | 0 | 0
| Gallons | Price per Gal |  | Total
Fuel |  |  | 0
| # of unit | Price per Unit |  | Total
|  | 0 | 0
|  | 0 | 0
|  | 0 | 0
|  | 0 | 0
|  | 0 | 0
|  | 0 | 0
|  | 0 | 0
|  | 0 | 0
Other |  |  | 0
Total |  |  | 0
On Site Task Mgr. | Cal St. John |  | Approved By: |  |  |  |  | Date: