## Sheet1
COGCC Orphan Well Program 1120 Lincoln St. Ste. 801 (303) 894-2100 (COGCC) Ext. 5105 (PM Ofc.) (970) 302-1024 (PM Cell) |  | Location Number |  | 312196 |  | DATE | 2020-03-06
[6 empty] | WELL NO. | 075-06281
|  | Contractor |  | Excell |  | HOURS | 7:30 | TO | 2:00
|  | WEATHER |  |  |  | COUNTY | Logan
|  | OWP Project Mgr. |  | Mike Hickey |  | CUSTOMER ORDER |  | PHAA 2020 072
|  | DIRECTIONS |  | Mount Hope Unit W 36
TIME | DAILY WORK RECORD
7:30 | Crew start.
7:40 | Rig start. Spot in rig and rig up.
8:20 | Rig in rig pump to load well.
9:05 | Well loaded. 10-12 BBLS. Set up for pressure test.
9:40 | Bradenhead test. Pass. No blow or vaccum 0 psig.
10:10 | Pressure test completed. Pass. Casing held 345 psig pressure for 15 minutes. Nipple up and install BOP.
11:15 | Pick up tubing off float trailer and trip into well.
11:55 | Tripped in 32 joints. EOT @ 968'.
12:10 | Rig in rig pump to circulate well. Roll out oil to clean water and shut down pump. Circulate again Monday morning.
12:25 | Rig down rig pump and drain pump and lines.
2:00 | Remove fluids from clean up tank. Install standing valve and secure wellhead. Pick up tools, clean up location, and depart.
Notes:
Tomorrow: Monday | Circulate well to clean up. Wireline to run CBL and shoot perfs. Set retainer @ 950' and cement. Set retainer @ 544' and cement. Cement surface plug from 50' to surface.
| Hours | Price/Hour | Total |  | POSITION | NAME | RIG | TRAVEL | TOTAL
| 0 | 0 | 0 |  | OPERATOR | Jacob |  |  | 0
|  |  | 0 |  | DERRICK | Manny |  |  | 0
|  |  | 0 |  | CREWMAN | Sal |  |  | 0
|  |  | 0 |  | CREWMAN |  |  |  | 0
|  |  | 0 |  | CREWMAN |  |  |  | 0
0
|  | 0 | 0 |  | WELL RECORD
|  | 0 | 0 |  | Type Well Head
|  | 0 | 0 |  | Packer Settings
|  | 0 | 0 |  | Type Packer
|  | 0 | 0 |  | No. Jts. Tubing
|  | 0 | 0 |  | Pump Out
|  | 0 | 0
|  | 0 | 0 |  | Size Rods | No.Rods | Size Subs | No.Sub
|  | 0 | 0
|  | 0 | 0
| Gallons | Price per Gal |  | Total
Fuel |  |  | 0
| # of unit | Price per Unit |  | Total
|  | 0 | 0
|  | 0 | 0
|  | 0 | 0
|  | 0 | 0
|  | 0 | 0
|  | 0 | 0
|  | 0 | 0
|  | 0 | 0
Other |  |  | 0
Total |  |  | 0
On Site Task Mgr. | Cal St. John |  | Approved By: |  |  |  |  | Date: