## Sheet1
CATAMOUNT ENERGY PARTNERS LLC.
Well Name: |  | DAVIS Gas Unit 2 | API # | 067-07882
Well Name: |  | IGW 150 | API # | 067-09603
Inspector: |  | Catherine Roy
Document Number: |  | 693903263
Corrective Action: |  | Erosional riling is occurring at the well pad entrance where soils were recently disturbed.
Mulch is present and it appears that seeding is conducted in the area. However, the area
is not stabilized
Stormwater controls need to be installed to stabilize erosion within the project area.
Correction Action Due: |  | 2021-07-07
Action Completed: |  | 2021-06-09
Action Taken: |  | Filled in riling, installed rock dams along drainage off of the location at the entrance.