## Sheet1
CATAMOUNT ENERGY PARTNERS LLC.
Well Name: |  | Harmon MVRD Unit 1 | API # | 067-05439
Inspector: |  | Catherine Roy
Date Inspected: |  | 2021-07-07
Document Number: |  | 693903368
Corrective Action: |  | Approximately 200 Russian knapweeds observed within the interim reclamation areas.
Revegetation is progressing in non-weedy portions.
Control weeds by 7/31/2021.
Correction Action Due: |  | 2021-07-31
Corrective Action: |  | An erosional channel approximately 12 inches wide and deep is forming within the
northern project area where concentrated runoff flows off of the working area.
Stormwater controls need to be installed to stabilize erosion within the northern project
area by 8/8/2021
Correction Action Due: |  | 2021-08-08
Action Completed: |  | 2021-07-30
Action Taken: |  | Treated Russian knapweed, will continue to monitor and treat as necessary.
Action Completed: |  | 2021-07-15
Action Taken: |  | Filled in channel and built a control berm across the channeling area.