## Sheet1
Arkoma Operations LLC
Well Name: |  | Herrera Unit B 1 | API # | 067-05379 | Location ID # | 325129
Inspector: |  | Catherine Roy
Date Inspected: |  | 2021-08-06
Date Submitted |  | 2021-08-12
Document Number: |  | 693903529
Corrective Action 1: |  | Tank containment berms are eroding resulting in reduced capacity, and are inadequate to
contain fluids
Repair or install berms or other secondary containment devices per Rule 603.o. by 9/11/2021. Berms need to be stabilized to prevent erosion.
Corrective Action 2: |  | Erosion is occurring on well pad cut and fill slopes, sediment is discharged from diversions,
and downcutting is occurring downstream from culvert outlet. All stormwater BMPs
observed are inundated and are not adequate/no longer functioning
Stormwater (i.e.: BMPs) and erosion controls (i.e.: erosion control blanket, hydro mulch, etc.)
need to be installed to stabilize erosion and prevent sediment discharge within the project
area, no later than 8/30/2021. Controls need to be selected, sized, installed, and
maintained according to good engineering practices such as those described by CDOT in
their erosion control manuals.
Correction Action Due 1: |  | 2021-09-11
Action Completed: |  | 2021-08-30
Action Taken: |  | Rebuilt tank containment berms.
Correction Action Due 2: |  | 2021-08-30
Action Completed: |  | 2021-08-30
Action Taken: |  | Dug diversion ditches on ROW to divert storm water to a natural drainage, cleaned the silt out of diversion ditches and built a silt pond
on the edge of the location. Installed rock check dams along the diversion ditches and downstream from culvert outlet.
Re-seeded the berms and bare slopes.