## Sheet1
Arkoma Operations LLC
Well Name: |  | Jaques 1 | API # | 067-05294 | Location ID: | 333792
Well Name: |  | Jaques 5F | API # | 067-07693 | Location ID: | 333792
Well Name: |  | Jaques 9 | API # | 067-10021 | Location ID: | 333792
Inspector: |  | Catherine Roy
Date Inspected: |  | 2021-08-11
Date Submitted: |  | 2021-08-18
Document Number: |  | 693903551
Corrective Action 1: |  | Gravel and road fill material are washed off of the access road, up to 50 feet down-slope.
Remove and properly manage/control discharged road materials from the access road.
Correction Action Due: |  | 2021-09-18
Action Completed: |  | 2021-09-17
Action Taken: |  | Removed road material, cleared out diversions and road cut outs.
Corrective Action 2: |  | Stormwater erosion is occurring along the majority of the access road where roadside
diversions are not adequately diverting flows which are running over the road surface and
eroding roadside slopes and depositing gravel and fill material offsite. Erosion is also
occurring within the southwestern corner of the project area where a channel is forming
along the pipeline ROW. Stormwater BMPs on well pad diversions are largely full of
sediment, wattles and straw bales are largely not functioning.
Stormwater erosion needs to be controlled along the access road. Stormwater controls
need to be installed to stabilize erosion within the southwestern project area. Additionally,
all stormwater BMPs within project diversions need maintenance and repair/and or
replacement. Corrective action date: 9/18/2021.
Correction Action Due: |  | 2021-09-18
Action Completed: |  | 2021-09-17
Action Taken: |  | Cleaned out and deepened roadside diversions and cut outs.
Cleaned out and improved diversion ditches along the ROW at the Southwester well pad,
Rock check dams were rebuilt and reinforced.
Reseeded bare ground along the western and southern portions of the well pad.