## Sheet1
ABUNDANCE ENERGY SERVICES, LLC
Well Name: | Jaques 6-F | API # | 067-07692 | Location ID # |  | 326237
| Jaques 12 |  | 067-10018 | Doc # | 714001761
| Jaques 11 |  | 067-10019
| Jaques 10 |  | 067-10020
Inspector: | Corey McDonough
Date Inspected: | 2025-01-24
Date Submitted: | 2025-01-30
Document Number: | 714001761
Corrective Action 1:
Correction Action 1 Due: | ASAP
Action Completed: | 2025-02-06
Action Taken: | Location signs were up-dated as soon as weather conditions would allow the stickers to adhear to the cold metal sign.
BEFORE PHOTOS |  |  |  | AFTER PHOTOS
Corrective Action 2:
Correction Action 2 Due: | ASAP
Action Completed: | 2025-02-27
Action Taken: | All weed debris has been removed from the project area. All areas with sparse vegetation within the reclamation area have been reseeded and mulched in an effort to establish desirable vegetation.
BEFORE PHOTOS |  |  |  | AFTER PHOTOS
Corrective Action 3:
Correction Action 3 Due: | ASAP
Action Completed: | 2025-02-27
Action Taken: | All erosional channeling within the project area has been repaired and BMP's installed where needed to help with future success.. Slopes have been seeded and mulched in an effort to establish desirable vegetation in these areas.
BEFORE PHOTOS |  |  |  | AFTER PHOTOS